## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1805709 |  |  | Week starting: | 2021-03-22
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-03-22 | 18:00 | 21:00 | 3 | Watch the lecture and fix my pitch | learn more about the pitch content | Fixed my pitch structure and content
Tuesday | 2021-03-23 | 9:00 | 12:00 | 3 | Organize application requirements and write the agenda for the client meeting | Explore the workflow of the application logic part and prepare for the meeting /milestone 1 | Have a general understanding of the logic judgment process of the application,the agenda passed team review
Wednesday | 2021-03-24 | 9:00 | 11:00 | 2 | Select and design data structure | Preparation for application's logical process /milestone 1 | Determined the required data structure and communicated with the team member in charge of the database
Thursday | 2021-03-25 | 10:30 | 12:00 | 1.5 | Attend the client meeting and write the minutes | Show the pitch to client and organize meeting results | Good feedback, going to take further practice
Friday | 2021-03-26 | 9:00 | 11:00 | 2 | Practice presentation | Prepare for the pitch presentation | Pitch presentation preparation is done
Saturday | 2021-03-27
|  |  | Total | 11.5