## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1805709 |  |  | Week starting: | 2021-03-29
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-03-29 | 9:30 | 11:00 | 1.5 | Record pitch presentation video | Finish the task of pitch presentation | The video is sucessfully recorded
Tuesday | 2021-03-30 | 8:00 | 13:00 | 5 | Complete the part that belongs to me in the business case & draft plan | Set the business case & draft plan as a draft guideline for the whole project | Pointed out the questions & solutions, defined Activities and Projected Outputs of the logic part, the team roles and communication plan is set
Wednesday | 2021-03-31 | 13:00 | 15:30 | 2.5 | Watch the lecture and fix the business case & draft plan | Get more information of the business case & draft plan and modify it | Shorten my parts of business case & draft plan in order to meet the requirement
Thursday | 2021-04-01
Friday | 2021-04-02 | 14:00 | 18:00 | 4 | Learn Javascript | Prepare for the logical determination workflow /milestone 1 | In the process of learning and experimenting, I found that the expected data structure is difficult to achieve and use, need to find a perfect alternative
Saturday | 2021-04-03
|  |  | Total | 13