## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1805709 |  |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-04-26 | 9:00 | 16:00 | 7 | Implement propagation and determination algorithms | Build algorithm for the alert /milestone 1 | Completed the structure of the algorithm
Tuesday | 2021-04-27 | 9:00 | 14:00 | 5 | Implement propagation and determination algorithms | Build algorithm for the alert /milestone 1 | Loop and logical judgment are implemented
Wednesday | 2021-04-28 | 13:00 | 15:00 | 2 | Organize the workflow, draw pictures, and add explanations | Prepare for the client meeting | Ready to explain my algorithm' working pattern and effectiveness to the client
Thursday | 2021-04-29 | 14:00 | 17:00 | 3 | Attend the client meeting and send client a detailed algorithm description | Confirm that existing algorithm and workflow are acceptable /milestone 1 | The algorithm and workflow are approved by the client
Friday | 2021-04-30 | 9:00 | 9:30 | 0.5 | Write my part of the milestone1 report | Finish milestone1 report | Passed team review
Saturday | 2021-05-01
|  |  | Total | 17.5