## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1805709 |  |  | Week starting: | 2021-05-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-17 | 15:00 | 17:30 | 2.5 | Attend lecture and read the testing plan requirement and our current testing plan | learn about testing plan and review current achievement | I have confirmed the part I am responsible for and have a clear idea, first continue to complete the debugging and construction of the algorithm
Tuesday | 2021-05-18 | 9:00 | 11:30 | 2.5 | Re-visite the requirements for the testing plan | This helps me better prepare for the testing. | Continue to revise our testing plan.
Wednesday | 2021-05-19 | 9:00 | 12:00 | 3 | Go back to the loop version and make changes | Find an appropriate way to use loops in JavaScript /milestone 2 | The loop worked as expected, but there are still problems with the subsequent synchronous to asynchronous conversion
Thursday | 2021-05-20 | 21:00 | 22:00 | 1 | Modify the code structure | Solve the problem of synchronous to asynchronous /milestone 2 | The code runs as expected
Friday | 2021-05-21 | 9:00 | 12:00 | 3 | Implement parameter control system | Add parameter control system /milestone 2 | The code runs as expected
Saturday | 2021-05-22
|  |  | Total | 12