## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1805709 |  |  | Week starting: | 2021-05-24
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-24 | 9:00 | 10:00 | 1 | Write test code | Prepare to test the algorithm | The testing file is done
Tuesday | 2021-05-25 | 12:00 | 13:30 | 1.5 | Write testing plan | Finish testing plan | My part of the testing plan is done and reviewed by team
Wednesday | 2021-05-26 | 9:00 | 12:00 | 3 | Create users and add information to the database, and do the test | Test the algorithm /milestone 2 & testing report | Finished testing, result are the same as expected, and the test report is filled
Thursday | 2021-05-27 | 12:00 | 13:00 | 1 | Read the requirement of the final report | Understand the final report | Understood the principles of the final report
Friday | 2021-05-28 | 8:00 | 10:00 | 2 | Attend the team meeting and write the agenda for the next client meeting | Assign work | The poster and demo are assigned to peers
Saturday | 2021-05-29
|  |  | Total | 8.5