## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID |  | a1805709 |  | Week starting: | 8/3/2021
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 8/3/2021 | 13:00 | 17:00 | 4 | Studying project information, and preparing for the first client meeting. | A general understanding of the project can help me better participate in the meeting, thereby improving the efficiency of the meeting. | Going to attend the meeting on Tuesday with prepared knowledge and questions.
Tuesday | 9/3/2021 | 15:00 | 18:00 | 3 | attending client meeting and summarise the meeting outcomes | It’s important to know what the client thinks about the projects. | Understood the project background, problems, and solution direction./ Going to set tasks by the summarized flow chart and prepare for the next meeting.
Wednesday | 10/3/2021 | 17:00 | 20:00 | 3 | attending workshop, and self-learning about pitch business | The pitch is important as a part of the project, it shows our understanding and exploration of the project. In the case of MCI project, our pitch is going to help client know that if we were on the track or not, which will increase the efficiency and outcome. | Know the issues that pitch should pay attention to, and the necessary content. Learned about the presentation skills./ Going to set task allocations by the necessary contents.
Thursday | 11/3/2021 | 11:00 | 11:30 | 0.5 | Identifying tasks and discuss task allocation with teammates. | Quantifying and assigning tasks can give us a clearer understanding of how to complete the entire project, which could lead to a better outcome. | Going to initially clarify tasks and their allocations.
Friday | 12/3/2021 | 15:00 | 17:00 | 2 | Making task allocation plan | Quantifying and assigning tasks can give us a clearer understanding of how to complete the entire project, which could lead to a better outcome. | Initially clarified tasks and their allocations.
Saturday | 13/3/2021 | 13:00 | 13:30 | 0.5 | Fix task allocation plan | Quantifying and assigning tasks can give us a clearer understanding of how to complete the entire project, which could lead to a better outcome. | Break down the milestones and further subdivide the tasks./start to work accroding to the plan and wait for next week's meeting.
|  |  | Total | 13