## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1770710 |  |  | Week starting: | 2021-03-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-03-08 | 9:00 | 10:00 | 1 | 1. Prepare questions for the client meeting 2. Prepare minutes template | I believe finishing these tasks can help me better understand and plan for the project. | After reading through project description, I listed 6 questions that I need to ask for clarification from the client. I also created a simplified template for the minutes of the meeting. After the meeting tomorrow, I will record the requirements/plans/actions in the minutes.
Tuesday | 2021-03-09 | 15:00 | 16:30 | 1.5 | 1. First client meeting 2. Summarise key information and prepare meeting minutes | These tasks helped our team to better understand the project and become clear on what needs to be done. | We had a productive conversation with the client and are clear on the tasks to be done for the week.
Wednesday | 2021-03-10 | 16:30 | 18:00 | 1.5 | 1. Study whether Cordova framework is suitable for the project. 2. Learn about presentation skills in workshop | 1. Studying Cordova helped us determine the most suitable framework/programming languages for this project. 2. I learned some presentation tips in the workshop. | 1. I discovered that Cordova is capable of meeting the requirements of the project. We will be using Cordova for this project. 2. We will start preparing for the pitch presentation soon.
Thursday | 2021-03-11 | 9:30 | 10:00 | 0.5 | Discuss Mockup issues with teammates | We decided what elements/pages should be included in the App. | My teammate created a sketch of the App. I will convert the sketch into a proper mockup using Adobe XD.
Friday | 2021-03-12 | 9:00 | 12:30 | 3.5 | Create the mockup using Adobe XD. | This gives us a clearer picture of what the App should look like and what functionalities it should provide. | I have created the first draft. Next, I need to review the draft, discuss with my teammates and fix the potential problems.
Saturday | 2021-03-13 | 9:00 | 9:30 | 0.5 | Fix problems in the mockup | I adjusted the App design to better fit the requirements. | I will share the mockup in the team drive.
|  |  | Total | 8.5