## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1770710 |  |  | Week starting: | 2021-05-03
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-03 | 15:00 | 16:30 | 1.5 | Attend the lecture; final review of milestone 1 report | This is the end of iteration 1; the lecture helped me to clarify requirements of different assignments. | I added new reflections to the report; I finished labelling files in GitHub.
Tuesday | 2021-05-04 | 9:30 | 11:30 | 2 | Start writing the plan for milestone 2. | We are currently in the preparation phase of iteration 2. | I completed most of the milestone 2 planning.
Wednesday | 2021-05-05 | 9:00 | 10:00 | 1 | Organise the files and information collected so far. | This helps me to wrap up the tasks so far and start the new iteration | I will start writing the testing plan tomorrow.
Thursday | 2021-05-06 | 8:00 | 11:00 | 3 | Write the testing plan. | This is one of the tasks of iteration 2. | I finished the project overview in the introduction section.
Friday | 2021-05-07 | 9:00 | 10:00 | 1 | Review and edit the project overview in the testing plan. | I am in the process of planning for the testing, which is one of the activities of iteration 2. | The project overview is officially done. Next I will move on to the definition of the testing scope.
Saturday | 2021-05-08 | 9:00 | 11:00 | 2 | Develop the scope of the testing. | I am in the process of planning for the testing, which is one of the activities of iteration 2. | I finished defining the testing scope.
|  |  | Total | 10.5