## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1770710 |  |  | Week starting: | 2021-04-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-04-19 | 9:00 | 11:00 | 2 | Add new server-side database interactions. | This improves the server and database interactions, which are part of the tasks for the first iteration. | I finished the functions I planned to add. I will continue to review and seek improvements.
Tuesday | 2021-04-20 | 10:00 | 11:00 | 1 | Add functions that can count the total number of contacts of the user | This helps with improving the database functions. It is part of the process for reaching milestone 1. | I finished defining and testing the new function.
Wednesday | 2021-04-21 | 21:00 | 22:00 | 1 | Improve database interaction functions based on teammate's requests. | This helps to make my part of the code cooperates better with my teammate's part. | I added the fields and functions my teammate requested.
Thursday | 2021-04-22 | 9:00 | 9:00 | 0 | break | break | break
Friday | 2021-04-23 | 9:00 | 11:00 | 2 | Improve database interaction functions based on teammate's requests; discuss about plans for merging; review my code and look for errors. | Preparation before merging with my teammates' code. | I added the fields and functions my teammate requested. I found that it is more convenient to have a field "contactCount" to store the total number of contacts in the past 14 days, so I added the field and adjusted related functions.
Saturday | 2021-04-24 | 9:00 | 10:00 | 1 | Learn about GitHub merging. | Part of the process for reaching milestone 1. | I learned how to merge branches and resolve conflicts.
|  |  | Total | 7