## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1770710 |  |  | Week starting: | 2021-04-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-04-12 | 8:00 | 8:00 | 0 | Break | Break | Break
Tuesday | 2021-04-13 | 10:00 | 11:00 | 1 | Start coding the functions for database interactions | Part of the process for reaching milestone 1. | Next, we will have a team meeting to clarify each team member's responsibilities.
Wednesday | 2021-04-14 | 21:00 | 12:00 | 3 | 1. Team meeting 2. Continue coding for the database | Part of the process for reaching milestone 1. | It is confirmed that I am responsible for making the server and the database. I finished most of the code for database interactions.
Thursday | 2021-04-15 | 9:00 | 13:00 | 4 | Code for the server | Part of the process for reaching milestone 1. | I found that Firebase may be more suitable for this project, so I switched our database choice from MongoDB to Firestore, rewrote some of the database functions and finished some code for handling requests to the server. I also wrote some front-end code that can interact with the backend.
Friday | 2021-04-16 | 9:00 | 11:00 | 2 | Continue coding for the database | Making progress towards reaching milestone 1 by completing the server and database. | I almost finished the client-side database interactions.
Saturday | 2021-04-17 | 9:00 | 11:00 | 2 | Continue coding for the database | Making progress towards reaching milestone 1 by completing the server and database. | I finished the server-side database interactions.
|  |  | Total | 12