## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1779212 |  |  | Week starting: | 2021-05-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-10 | 15:00 | 16:00 | 1 | Attend the lecture. | Get review on our report and advices on plan. | Accept the new arrangement for lecturer meeting.
Tuesday | 2021-05-11 | 11:00 | 15:00 | 4 | QR code generating function programming. | To generate a qr code which contained the contactor ID. | Looking for another plugin.
Wednesday | 2021-05-12 | 13:00 | 16:00 | 3 | Bugs fixs on generating function. | The code won't display on the UI. | Solved the problem of not generating qr code by using API.
Thursday | 2021-05-13 | 10:00 | 14:00 | 2 | QR code scanning function programming. | To read the qr code which scanned by the phone. | Most of the functions works.
Friday | 2021-05-14 | 11:00 | 13:00 | 2 | Add firebase API into scanning function. | Upload the contactor information which scanned the code. | API added.
Saturday | 2021-05-15 | 3:00 | 4:00 | 1 | Bugs fixs on scannting function. | The function got some repeated objects. | Clean up the object everytime the function finished running.
|  |  | Total | 13