## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1770710 |  |  | Week starting: | 2021-05-24
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-24 | 15:00 | 16:30 | 1.5 | Final review of the testing plan; attend lecture; | This is the end of the test planning process. | Start writing the testing report.
Tuesday | 2021-05-25 | 14:30 | 22:00 | 7.5 | Code for the front-end | Part of the front-end fixing process for iteration 2. | I have finished transfering most of our front-end interfaces to HTML, CSS and JS.
Wednesday | 2021-05-26 | 8:30 | 11:30 | 3 | Code for the front-end | Part of the front-end fixing process for iteration 2. | I finished transfering the whole front-end to HTML, CSS and JS. Now the functionalities that couldn't work due to the limitations of Vue are working.
Thursday | 2021-05-27 | 21:00 | 22:00 | 1 | Start preparing for the final report. | This is the task for wrapping up the project. | I created the structure of the report and filled in it some initial thoughts.
Friday | 2021-05-28 | 8:00 | 9:30 | 1.5 | Continue to work on the final report; team meeting | Preparing for the poster/demo and final report. | We finished allocating works for the poster/demo.
Saturday | 2021-05-29 | 9:00 | 11:00 | 2 | Prepare for the poster. | In the process of wrapping up the project. | I finished most parts of the poster that I'm responsible for.
|  |  | Total | 16.5