## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1784184 |  |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-04-26 | 13:00 | 15:00 | 2 | Front-end coding | In order to build a simple front-end interface to achieve the goal of Milestone1. | Use JavaScript to add actions to each page to achieve the desired function.
Tuesday | 2021-04-27 | 14:00 | 17:00 | 3 | Test the front-end by using chrome and prepare for milestone 1 report. | To reach the milestone 1 | Tested each function with a browser, and ensured that the logic is basically correct, and made some modifications based on the information provided by the console.
Wednesday | 2021-04-28 | 16:00 | 17:00 | 1 | Attend the workshop | Learn some detail information about milestone 1 report . | Edited the milestone 1 report by following instruction .
Thursday | 2021-04-29 | 15:00 | 17:00 | 2 | Preparation and client meeting | Front-end achievement display | Got some suggestion from the client about front-end in misspellings, page transition problems and display of incorrect information.
Friday | 2021-04-30 | 9:00 | 10:30 | 1.5 | Milestone 1 report writing. | To finish the iteration 1 project management. | Milestone 1 has been finished after submission.
Saturday | 2021-05-01 | 21:00 | 22:00 | 1 | Preparation for the next milestone. | Start to work on testing plan. | Reviewed the example provided by lecturer. Start the next work in next week.
|  |  | Total | 10.5