## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID |  | a1779212 |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 12:00 | 17:00 | 5 | Bluetooth scanning and advertising function coding. | To reach milestone 1. | Basic function finished.
Tuesday | 2021-04-27 | 11:00 | 14:00 | 3 | Fix the bugs and test the bluetooth function. | To reach milestone 1. | Bugs fixed and test finshed.
Wednesday | 2021-04-28 | 15:30 | 16:30 | 1 | Attend workshop. | Learn about some details of what we need to do in milestone 1 report. | Complete the milestone1 report with my teammates.
Thursday | 2021-04-29 | 16:15 | 16:50 | 0.5 | Client meeting. | Show client what we have done yet. | Got some feedback from client and planned to improve the application.
Friday | 2021-04-30 | 14:30 | 15:00 | 0.5 | Final review on milestone1 report. | Make sure everythings are correct. | Milestone 1 report submitted.
Saturday | 2021-05-01 | 13:00 | 14:00 | 1 | Prepare for milestone 2. | Make some further process on the project. | Milestone 2 example reviewed.
|  |  | Total | 11