## Sheet2
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1784184 |  |  | Week starting: | 2021-05-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-05-17 | 15:00 | 16:30 | 1.5 | Attend lecture | Learn about PM. | Know project management and software development process better.
Tuesday | 2021-05-18 | 16:00 | 18:00 | 2 | Clarify the testing plan | Finish testing better. | Will still writing the testing plan next.
Wednesday | 2021-05-19 | 10:00 | 12:00 | 2 | Writing on the testing plan | Finish testing better. | Found some ways to show our testing progress better.
Thursday | 2021-05-20 | 21:00 | 22:00 | 1 | Writing on the testing plan | Finish testing better. | Finished my part of testing plan.
Friday | 2021-05-21 | 15:00 | 17:00 | 2 | Group meeting | Fuction merging for final testing. | Cannot be merged, keep working to figure the main issue out.
Saturday | 2021-05-22 | 9:00 | 11:00 | 2 | Fix the issue of the problem that the front end cannot be connected to the plug-in | Fuction merging for final testing. | I found some similar cases where the Vue code cannot use the cordova plug-in. I tried a solution, but it didn't work. Considering whether to use cordova framework to rewrite the front end
|  |  | Total | 10.5